Open Source Geospatial Foundation

Request for Proposals for FOSS4G 2020

Contents

2. Key Info
Conference Title	FOSS4G 2020
Conference Year	2020
Conference Region	North America
Conference number	14
Authors	Till Adams, Steven Feldman, Michael Terner
Conference Committee Chair	Till Adams (till.adams@fossgis.de)
Conference Development Mail List	conference_dev@lists.osgeo.org
Version date	2018-09-01
RfP Document repository	http://svn.osgeo.org/osgeo/foss4g/rfp/2020/

Key Dates
Request for Proposals released	2018-09-14
Stage 1
Letters of Intent submitted to Conference Mailing List by 2400 GMT	2018-10-05
Period for questions to bidders	2018-10-06 to 2018-10-12
Conference Committee votes on Letters of Intent	2018-10-13 to 2018-10-18
Selected Letters of Intent are notified and requested to submit full proposals	2018-10-19
Stage 2
Full Proposals submitted to Conference Mailing List by 2400 AoE[1]	2018-11-23
Period for questions on proposals	2018-11-24 to 2018-11-30
Conference committee meeting to discuss Proposals	Approx 2018-12-03
Time for final clarifications
Conference Committee voting ends by 2400 GMT	2018-12-12
Recommendation made to OSGeo Board but not published	2018-12-13
Selection of host city announced by Board of OSGeo	Approx 2018-12-19
[1] https://en.wikipedia.org/wiki/Anywhere_on_Earth

All dates are in ISO-8601 format (YYYY-MM-DD)
The Conference Committee reserves the right to adjust these dates and will notify any changes of dates on the Conference Mailing List.
Purpose
This document provides the background to the OSGeo Foundation’s FOSS4G Conference and sets out the requirements and process for prospective bidders to host FOSS4G 2020.
1. Background
  1. About OSGeo
The Open Source Geospatial Foundation (http://www.osgeo.org/) is a volunteer run not-for-profit organization whose mission is to support and promote the collaborative development of open geospatial technologies and data. The Foundation provides financial, organizational, and legal support to the broader open source geospatial community. It also serves as an independent legal entity to which community members can contribute code, funding, and other resources secure in the knowledge that their contributions will be maintained for public benefit. OSGeo also serves as an outreach and advocacy organization for the open source geospatial community and provides a common forum and shared infrastructure for improving cross-project collaboration. The Foundation's projects are all freely available and usable under OSI-certified open source licenses.
  1. Conference History
The global FOSS4G conference and its predecessors have been the annual OSGeo “meeting of the tribes” for Geospatial Open Source projects and communities. For a history of prior events see https://wiki.osgeo.org/wiki/FOSS4G and https://wiki.osgeo.org/wiki/Past_FOSS4G_Reports )

About FOSS4G
The Open Source Geospatial Foundation (OSGeo) aims for each year’s Global FOSS4G to be the geospatial conference of the year. In line with OSGeo goals, this conference will promote open source geospatial technologies and data.
  1. Conference Attendance
Conference attendance has grown consistently over the last decade and the hope is that the next conference will continue this momentum. Historically, the majority of attendees (60-70%) come from within the region hosting the conference.
- European and North American events have recently attracted 950-1200 delegates[2]. Future events are hoped to attract 1000+ attendees
  [2] Some historic delegate information is at https://docs.google.com/spreadsheets/d/1ux_hFq-C165140ZD48RRImPTHSpXj42OG3nBr9cyZYo/edit#gid=1782600951
- Rest of World events have attracted 450-600 delegates, exception was Dar Es Salaam with > 1000 delegates. Future event sizes are likely to be predominantly determined by the size of the local community.
  1. Conference Structure
Previous FOSS4G conferences have had the following general components. While this should be used as a guide, variations or alternatives may be proposed. The conference structure has evolved over time and we welcome further innovation in future proposals.
- 2 days of workshops.
  - Attended by 200 to 300 people across all workshops, depending on facilities.
  - Workshops are generally 3.5 - 4 hour instructional sessions, in a computer lab setting -
  - Normal workshop sizes are 20-30 attendees/workshop
  - We advise that labs should have good specification computers ready for workshops. “Bring Your Own” can cause time loss because software has to be installed by delegates and individuals’ machines may not be of adequate specification. You should indicate whether workshop computers will be provided.
  - Workshop instructors provide software, data, and materials.
  - Some conferences have provided free entry for workshop presenters while others have not, you should clearly state what your policy will be. The instructor payment (or not) policy should also be stated in the call for workshop instructors for your event.
- Three days of the “main conference”.
  - Attended by 500-1,200 people, depending on conference attendance.
  - Opening and closing plenary sessions with all attendees at the start and end.
  - Sometimes additional plenary sessions at the start and/or end of conference days.
  - Approximately six to nine parallel tracks of presentations, with each presentation typically consisting of a 20-minute talk, 5 minutes of Q&A, and 5 minutes of transition time between talks.
  - You should detail catering arrangements (usually coffees, water and lunches are provided) and confirm that provision will be made for dietary restrictions and allergies.
- An “academic track”, with paper selection organized by an academic committee and possibly a journal for publication of proceedings.
- A code sprint, held before, during and/or after the conference. Interested developers join together for day(s) of programming.
  - Venue could be outside of main conference venue in order to reduce costs.
  - Consider some catering for the sprinters.
- Most of the recent conferences have included a Business to Business (B2B) event as part of the proceedings, and your team is encouraged to consider including this type of event, favourite is the day before the official conference starts (2nd workshop day).
- Streaming and archiving all conference proceedings
  - Most conferences have recorded all of the conference proceedings and archived the video to enable those not able to attend the conference to view plenaries and talks of interest. See http://video.foss4g.org
  - More recently conferences have offered live streaming which offers a remote participation option. This functionality is desired if the local infrastructure will support it.
  - You should clearly explain your plans for recording the conference and whether you will seek financial support from OSGeo (see Video below)
- Social events
  - An “ice breaker” event on the evening before or on the first day. Usually held in a large bar or restaurant, but could be in any venue that allowed for easy mixing and mingling.
  - A “gala” event on the evening of the first or second day. Usually held in a “showcase” venue which ideally should be able to accommodate all delegates. Examples have included: an art museum, a castle, a harbor/ship cruise, a cultural restaurant and a giant marquee.
  - It is preferable that social events are included within the conference ticket price, if you propose to charge delegates for any of the social events in your proposal you must detail this in your proposal.
- OSGeo Community events and activity
  - The OSGeo Annual General Meeting. The AGM includes short presentations from local chapters, the board, and other speakers on the state of OSGeo. Held in a venue suitable for about 200 people and scheduled for 1-2 hours on one of the main conference days (not at the beginning or at the end). No other programming should be scheduled during the AGM.
  - The Sol Katz Award, presented during the closing plenary session. The award is selected and presented by the Sol Katz committee, the conference organizers should include 15 minutes in the closing plenary schedule for the presentation.
  - Student awards are funded and selected by the OSGeo educational team, Geo4All or the Academic Track Committee. Allow 15 minutes in the program for these awards. You will need to appoint a member of your LOC to liaise with Geo4All.
  - Birds of Feather Sessions. Groups self-organize to discuss topics of common interest. Suggest times between the program, typically after presentations complete, but can also include breakfasts or dinners. Suggest locations such as lecture rooms or local pubs.
  - OSGeo Directors Face-to-Face Meeting. Typically, a 4 hour meeting held before or after the conference, in a boardroom or meeting room within the conference venue or nearby.
  - Some events have run a Map Gallery or competition.
  - All event publicity and branding should make clear that OSGeo is the organisation behind the LOC.
    - Opening and closing sessions should make mention of OSGeo’s role.
    - The opening keynote should have an OSGeo related topic (community, organization, some OSGeo project, open source geospatial software,...).
- Exhibition – an exhibition area for sponsors, usually close to beverage and catering services
  - An exhibition space/booth of equivalent size and prominence/location to the highest level of sponsor should be provided for OSGeo at no cost
- Commitment to Diversity and Inclusion.
OSGeo seeks to extend the diversity and inclusiveness of its activities. To further this objective, proposals should:
  - Confirm that the OSGeo Code of Conduct http://www.osgeo.org/code_of_conduct/ will be considered the start of a framework Code of Conduct for FOSS4G with appropriate additions based on the local environment agreed with the OSGeo Board or delegated committee.
  - Confirm a commitment to support the widening of access for all at FOSS4G through both the Travel Grant Program and within the program controlled by the proposed LOC.
  - Confirm a commitment to achieving a gender and race balanced plenary program.
  - Comment on alignment of OSGeo’s code of conduct with local laws and customs in relation to measures such as the Human Freedom Index: https://www.cato.org/human-freedom-index.
  1. More Conference Information
Prospective bidders are advised to review the following before submitting Letters of Intent or Proposals:
- The FOSS4G Handbook at https://wiki.osgeo.org/wiki/FOSS4G_Handbook
- The OSGeo Conference Committee wiki at https://wiki.osgeo.org/wiki/Conference_Committee
- The OSGeo Conference mailing list at http://lists.osgeo.org/mailman/listinfo/conference_dev (you must subscribe to be able to post to the list) or http://osgeo-org.1560.x6.nabble.com/OSGeo-Conference-Committee-f3721662.html (both have the same content, the latter may be easier to browse)
- Reports of past conferences https://wiki.osgeo.org/wiki/Past_FOSS4G_Reports
- Prior FOSS4G Lessons Learned: https://wiki.osgeo.org/wiki/Category:FOSS4GLessonsLearned
- Conference web sites in the format yyyy.foss4g.org e.g. http://2017.foss4g.org
- Document repository. Includes past bids, program books, sponsorship prospectuses, logo files, etc. http://svn.osgeo.org/osgeo/foss4g
Support by OSGeo
It is anticipated that the conference effort will be split into a local organizing committee (LOC) responsible for all work on venues, with the OSGeo Conference committee providing support, advice and access to past Chairs.
It is considered advantageous if key members of the LOC have demonstrated commitment and experience, such as shown by running a successful local or regional FOSS4G event. Ultimately the success of the event depends on a strong LOC that has a clear vision of the event they wish to build and the range of skills and time availability to pull everything together.
Most conferences are assisted by a professional conference organizer (PCO), this is up to the discretion of the LOC.
A FOSS4G is run by a LOC on behalf of OSGeo. You will need a legal organization (OSGeo Chapter, PCO etc) to contract with the venue and other suppliers.
Funding by OSGeo and distribution of surplus
It is expected that all FOSS4G events will be budgeted and operated to deliver a surplus over costs. Part of the surplus will be donated to OSGeo.
Seed Funding
OSGeo can offer seed funding (an advance to cover start-up expenses and deposits before revenues are received) and an additional guarantee to cover losses (up to an agreed limit) in the event of unexpected events (subject to approval of budgets and regular financial updates to an OSGeo board representative).
If OSGeo provides seed funding and guarantees, it is expected that in the region of 85% of any surplus generated will be donated to OSGeo (a lower percentage will be considered for events hosted in Lower or Middle Income economies). OSGeo will provide a financial supervisor who must be consulted on all major financial decisions. For more information see https://wiki.osgeo.org/wiki/FOSS4G_Handbook#Finances
If a LOC does not require seed funding or guarantees from OSGeo, they will be expected to donate at least 50% of the surplus after costs to OSGeo.
Travel Grant
OSGeo will provide a grant of $10,000 minimum towards a Travel Grant Programme (see https://www.osgeo.org/initiatives/foss4g-travel-grant-program/ ), the LOC are expected to raise at least an equivalent amount of funding through sponsorship, donations at registration or other means.
Video
OSGeo may provide loan funding towards the cost of recording the conference proceedings. If there is surplus from the conference, OSGeo requires this funding to be repaid in full to OSGeo before any calculation and distribution of the conference surplus.
1. Application Process
  1. Conference Region
The OSGeo conference committee has decided to solicit proposals from specific regions each year. The sequence is:
- 2016 - Europe ~ Bonn, Germany
- 2017 - North America ~ Boston, USA
- 2018 - other Regions ~ Dar es Salaam, Tanzania
- 2019 - Europe ~ Bucharest, Romania
- 2020 - North America
- 2021 - other Regions
- 2022 - Europe
  1. Stage 1: Letter of Intent
“Letters of Intent" will be accepted from potential Local Organizing Committees (LOC) in the conference region. If there are no submissions from groups in that region, letters from any region around the world will then be solicited.
    1. Dates
The timeline of the LoI and Proposal process and all deadlines are detailed in the section above.
    1. Requirements
“Letters of Intent" are limited to a maximum of two (2!!) pages, and should answer the following questions:
  1. Who is your conference chair?
  2. Who else is on your local organizing committee (LOC)?
  3. What is the experience of your committee members with similar events?
  4. What is your proposed venue? (include access to Internet, room sizes, maximum attendees)
  5. What are your provisional dates for the conference?
  6. Early thoughts on prices of conference attendance? (indicative estimates)
  7. What is the price range and general location of your proposed accommodations? (hotels)
  8. Are you partnering with other local organizations?
  9. What makes FOSS4G in your proposed location and with your team compelling?
    1. Submission and Due Date
Letters of Intent should be submitted in PDF format only to the Conference Mailing List (see above).
The deadline for submission is detailed in above.
    1. Committee Question Period
A period between the Letter of Intent closing date and the Stage 1 decision date will be used by the committee to ask for further information regarding the potential bids (see above). Questions will be asked on the Conference Mail List. List participants may also ask questions.
We expect at least one member of the LOC being on that list (in the past it has usually been the chair) and able to respond quickly.
    1. Committee Decision
If more than one Letter of Intent is received, members of the OSGeo Conference Committee will vote by each member voting for each LoI or abstaining. All LoI’s that receive at least 50% support (as measured by the number of conference committee members voting) will proceed to the next stage.
The committee reserves the right to extend the selection deadline and solicit additional proposals at its discretion.
  1. Stage 2: Bid Submission
Once your Letter of Intent has been accepted you must then submit a full proposal, as outlined next. If only one letter is received in Stage 1, a full proposal is still required.
You are advised to read one or two successful Proposals from previous FOSS4G selection processes, see https://wiki.osgeo.org/wiki/Conference_Committee
  1. Key elements for inclusion in your proposal
Your proposal should not exceed 50 pages including images, graphics and appendices. The conference Committee are seeking clear information that assists us in choosing between proposals, there is no need to invest time or resources in elaborate design.
Stage 2 respondents interested in hosting FOSS4G should provide the following information. In order to make proposals comparable, your proposal must have the following sections in this order.
1. Your reasons for hosting the conference, and your goals for FOSS4G.
1. How will your conference succeed financially (making a profit)?
2. How will your conference succeed socially (giving people the unstructured space and time to meet and engage with one another)?
3. How will your conference provide open source education (providing good training opportunities to new users)?
4. How will your conference promote open source geospatial software (bringing new organizations into the open source community)?
5. How will your conference promote inclusivity (welcoming a diverse community, students and those from lower income countries)?

2. The hosting location.
1. What city will the conference be in, what is interesting about it?
2. Are there any legal or cultural restrictions to attending the conference? (VISA, unsafe environment, religious restrictions, can a woman travel alone, cultural specifics, LGBTQi+ laws,...)
3. What venue will the conference be in, what are the number of rooms available, seating, and associated pricing?
4. Available workshop facilities, number of rooms, computers per room, pricing, strategy for providing workshop facilities.
5. Available rooms for additional small business meetings.
6. What accommodations are available? Where are they relative to the venue? Pricing? Quantity?
7. What is the maximum size your venue could entertain? The minimum?
8. How accessible is your venue? (wheelchair, blindness,...)
9. Will your venue have childcare facilities? With what requirements? (extra cost, age of children, schedule,...)
10. Will the conference have translation services? (optional)

3. The hosting organization and local community.
1. Supporting local organizations (companies, universities, user groups) and individuals that would be involved in the local conference committee, and a sense of their level of commitment.
2. Local organizing committee.
3. Local open source development and implementation activity, interest and enthusiasm for open source geospatial in your region.
4. How do you plan to manage/organize work and relations with OSGeo (especially with the board and conference committees)?

4. The budget.
1. What is your budget? Expenses for venue, food, marketing, audio-visual, network access, video streaming and/or recording etc
2. What is your expected attendance? Why? Where do you think delegates will come from?
3. What is your expected sponsorship? Why? Do you have local potential sponsors already identified? At what levels?
4. Delegate fees for the conference, workshop and any social activities not included in the main conference fee. We encourage you to consider innovative pricing plans that support inclusion of economically disadvantaged groups.
5. You should include detail of any grants or subsidized rates that you will offer which will be funded from within your budget (note that you will be expected to part finance and run a Travel Grant Programme with support from the Conference Committee)
6. Estimate of any seed funding and/or guarantee required
7. The level of surplus forecast at different levels of attendance and the proportion that will be donated to OSGeo (see Funding by OSGeo and distribution of surplus)

Include a high level budget summary within your proposal and also provide a separate detailed budget as detailed in the section below.

5. The program (see above)
1. Provide a high-level view of the program, indicating number of tracks, size of tracks, workshops, size of workshops, and other features of your program. Indicate the number of presentations, posters, and workshops you expect to accept.
2. What social events will be part of the schedule?
3. What dates do you expect to run the conference? Are they adjustable?
4. Provide a list of local/regional/international conferences around the selected date that are viewed as competition or collaboration.

The Conference Committee welcomes innovation in the structure and content of the conference program.

6. Other
Other relevant details (ie. do you plan to use professional conference organizing service, and approximate cost).
    1. Budget
A budget template is available to download from the RfP Document Repository (see Key Info above).
You must include a budget with your submission. You may provide more detailed information than the minimum set out within the template. You must also provide a risk assessment including cancellation costs in the last 3 months.
Please provide your budget in US dollars and confirm the date of any currency rate assumption.
  1. Other considerations
    1. Timing
Past FOSS4G conferences have been held during the August-September period and some continuity is desirable. However, other dates are possible, as long as you give yourself enough time to attract sponsors. Please propose a date for the conference, as well as the reasoning for your date selection (keeping in mind public holidays, regional vacation periods and related conference conflicts or synergies).
    1. Conference Naming
The conference name will be “FOSS4G <city name> <year> hosted by OSGeo”. Other variants of the name may be considered, for translation purposes.
    1. Conference Logo
For continuity, the conference logo used must contain a variation of the FOSS4G “ribbon”. You can view how past organizing committees used the ribbon in their design at www.foss4g.org
    1. OSGeo Code of Conduct (CoC)
Like all OSGeo activities, FOSS4G is subject to the OSGeo Code of Conduct, http://www.osgeo.org/code_of_conduct. The LOC is responsible for making the CoC a visible part of FOSS4G, as well as handling any CoC-related concerns related to the event.
Socializing
Please have in mind, that FOSS4G is also a gathering of people, many of whom only meet once a year. Hints on places (restaurants, pubs, bars, etc.) where people can meet during the conference days are welcome!
  1. Evaluation Criteria
The responses will be evaluated by the conference committee and a recommendation made for selection to the OSGeo board.
Criteria affecting selection will include:
- A sense of local capabilities (number of volunteers, committee members, experience, commitment, understanding of details) to pull off the conference.
- Suitability of the proposed facilities for hosting a conference.
- Ability to host several hands-on workshops.
- Size of conference that could be hosted?
  - Up to 1000 and more in North America and Europe
  - Potentially less (ca 500-700) in some Rest of World Locations
- Availability of a variety and suitable quantity of accommodation (some inexpensive accommodation is also desirable).
  - All accommodation should have minimal security requirements. Eg. if delegates have to share a hostel room, there should be a storage locker.
- Reasonable transportation to and around the conference venue.
- Cost for attendees
  - We hope to keep cost per participant under $650 USD for the conference (plus workshops).
  - We would welcome innovative approaches that can offer more affordable options to delegates. These might include differential pricing, alternative venues, reduced catering costs, changing dates or excluding the cost (or part of the cost) of social events.
  - Note: please include all prices in USD in your proposal, and please specify a currency date in your proposal (e.g. USD 2015-07-01).
- Provision of streaming (optional)
- Video recording and archiving (expected)
- Interestingness of meeting locale.
- Involvement by the various sector types (local committee should include private and public sector interests).
- Clarity on financial responsibility
  - A sense of the reliability and plausibility of budget estimates provided
  - Does the conference require seed funding and/or a guarantee from OSGeo?
  - The level of surplus to be returned to OSGeo
  - Does the conservative budget estimate result in a reasonable profit.

    1. Submission and Due Date
Your proposal should be submitted in PDF format only to the Conference Mailing List (see above).
If there are any sensitive attachments or appendices to your proposal (e.g. detailed budget) that you would prefer not to be made public please mail these to the Conference Chair (see above). These will be circulated privately to conference committee members and will not be posted to the mailing list
The deadline for submission is detailed in above.
    1. Committee Question Period
A period between the submission closing date and the decision date will be used by the committee to ask for further information regarding proposals; the question period is detailed in above. Questions will be asked on the Conference Mail List. List participants may also ask questions.
We expect at least one member of the LOC being on that list (in the past it has usually been the chair) and able to respond quickly.
Following the question period, the conference committee will convene a call to discuss the proposals and some further questions may follow this call before the committee votes.
  1. Committee Decision Method
The OSGeo conference committee members will have a first and second vote for proposals. 1st votes will be counted, if there is a tied result, second choice votes will be added to first choice votes for the tied bids from the first round only. In the event that there is still a tie the result will be determined by a published random process (see the FOSS4G Handbook for details).
The evaluation criteria have no fixed weighting and are used as a general guide.
    1. Committee Decision
Members of the OSGeo conference committee will vote after the question period ends to select the best proposal based on the evaluation criteria. Exact voting results will not be released. The conference committee will then propose the location to the OSGeo Board, who must formally approve of the decision.
The date of the final decision is detailed in above.
    1. Committee Discretion
The Conference Committee may vary this RfP process at its discretion. Any material variation will be dependent upon a majority private vote of the Conference Committee and a quorum of at least 5 members.
1. Post decision
  1. Complete Seed Funding and/or Guarantee Agreement
If a bidder has indicated that they wish to receive seed funding or a partial guarantee from OSGeo, the Conference Committee will draft a Finance Advance Agreement (based on those previously used e.g. https://svn.osgeo.org/osgeo/foss4g/2016/budget_planning/osgeo-local-committee-advance-agreement.odt ) for signature by the board and the LOC or their PCO.